## Listing
4 blocking open item(s), 5 major open item(s), 3 minor open item(s).
					Open items
id	type	priority	title	description	milestone	status		Blocking	Major	Minor
1	Enhancement	Blocking	Setup GUI	Create all basics buttons, without attached functionality, so as to test GUI library.	0.1	WIP		0	0	0
2	Enhancement	Blocking	Basic media play	Play, and stop media file reading	0.2	Open		1	0	0
3	Enhancement	Blocking	Advanced media play	Speed and start point can be set	0.2	Open		1	0	0
4	Enhancement	Blocking	Chapters	Chapters creation, display and modification through GUI	0.3	Open		1	0	0
5	Enhancement	Blocking	Save project to file	Project file will contain chapters. Link to media file should be updatable	0.3	Open		1	0	0
6	Enhancement	Major	Undo/Redo	implement history	0.3	Open		0	1	0
7	Enhancement	Major	mkv usage	store everything inside an mkv container, so that chaptering is not separated from media file	0.4	Open		0	1	0
8	Enhancement	Major	Translation support	Introduce capacity to localize software	0.5	Open		0	1	0
9	Enhancement	Major	Web hosting	Look for web hosting, bug tracking, source code sharing with Git or equivalent	0.5	Open		0	1	0
10	Enhancement	Minor	Open recent	Remember which projects were opened recently, for quick access	0.6	Open		0	0	1
11	Enhancement	Minor	History	GUI access to history of modifications	0.6	Open		0	0	1
12	Enhancement	Minor	GUI features	movable toolbars, explorer, etc	0.6	Open		0	0	1
13	Enhancement	Major	Speed-up	Add mode for repetition, that would play the selected section, first time at a given speed then faster and faster to desired speed	0.6	Open		0	1	0
14					Open		0	0	0
15					Open		0	0	0
16					Open		0	0	0
17					Open		0	0	0
18					Open		0	0	0
19					Open		0	0	0
20					Open		0	0	0
21					Open		0	0	0
22					Open		0	0	0
23					Open		0	0	0
24					Open		0	0	0
25					Open		0	0	0
26					Open		0	0	0
27					Open		0	0	0
28					Open		0	0	0
29					Open		0	0	0
30					Open		0	0	0
31					Open		0	0	0
32					Open		0	0	0
33					Open		0	0	0
34					Open		0	0	0
35					0	0	0
36					0	0	0
37					0	0	0
38					0	0	0
39					0	0	0
40					0	0	0
41					0	0	0
42					0	0	0
43					0	0	0
44					0	0	0
45					0	0	0
46					0	0	0
47					0	0	0
48					0	0	0
49					0	0	0
50					0	0	0
51					0	0	0
52					0	0	0
53					0	0	0
54					0	0	0
55					0	0	0
56					0	0	0
57					0	0	0
58					0	0	0
59					0	0	0
60					0	0	0
61					0	0	0
62					0	0	0
63					0	0	0
64					0	0	0
65					0	0	0
66					0	0	0
67					0	0	0
68					0	0	0
69					0	0	0
70					0	0	0
71					0	0	0
72					0	0	0
73					0	0	0
74					0	0	0
75					0	0	0
76					0	0	0
77					0	0	0
78					0	0	0
79					0	0	0
80					0	0	0
81					0	0	0
82					0	0	0
83					0	0	0
84					0	0	0
85					0	0	0
86					0	0	0
87					0	0	0
88					0	0	0
89					0	0	0
90					0	0	0
91					0	0	0
92					0	0	0
93					0	0	0
94					0	0	0
95					0	0	0
96					0	0	0
97					0	0	0
98					0	0	0
99					0	0	0
100					0	0	0
101					0	0	0
102					0	0	0
103					0	0	0
104					0	0	0
105					0	0	0
106					0	0	0
107					0	0	0
108					0	0	0
109					0	0	0
110					0	0	0
111					0	0	0
112					0	0	0
113					0	0	0
114					0	0	0
115					0	0	0
116					0	0	0
117					0	0	0
118					0	0	0
119					0	0	0
120					0	0	0
121					0	0	0
122					0	0	0
123					0	0	0
124					0	0	0
125					0	0	0
126					0	0	0
127					0	0	0
128					0	0	0
129					0	0	0
130					0	0	0
131					0	0	0
132					0	0	0
133					0	0	0
134					0	0	0
135					0	0	0
136					0	0	0
137					0	0	0
138					0	0	0
139					0	0	0
140					0	0	0
141					0	0	0
142					0	0	0
143					0	0	0
144					0	0	0
145					0	0	0
146					0	0	0
147					0	0	0
148					0	0	0
149					0	0	0
150					0	0	0
151					0	0	0
152					0	0	0
153					0	0	0
154					0	0	0
155					0	0	0
156					0	0	0
157					0	0	0
158					0	0	0
159					0	0	0
160					0	0	0
161					0	0	0
162					0	0	0
163					0	0	0
164					0	0	0
165					0	0	0
166					0	0	0
167					0	0	0
168					0	0	0
169					0	0	0
170					0	0	0
171					0	0	0
172					0	0	0
173					0	0	0
174					0	0	0
175					0	0	0
176					0	0	0
177					0	0	0
178					0	0	0
179					0	0	0
180					0	0	0
181					0	0	0
182					0	0	0
183					0	0	0
184					0	0	0
185					0	0	0
186					0	0	0
187					0	0	0
188					Rejected		0	0	0
189					0	0	0
190		Major					0	0	0
191					0	0	0
192					0	0	0
193					0	0	0
194		Trivial					0	0	0
195					0	0	0
196	Defect					0	0	0
197					0	0	0
198	Enhancement	Blocking					0	0	0
199					0	0	0
200					0	0	0
					0	0	0
					4	5	3
	Enhancement	Blocking				Open
	14	6				33
	Defect	Major				WIP
	1	6				1
		Minor				Done
		3				0
		Trivial				Rejected
		1				1

## Resources
Type	Priority	Milestone	Status
Enhancement	Trivial	0.1	Open
Defect	Minor	0.2	WIP
	Major	0.3	Done
	Blocking	0.4	Rejected
		0.5
		0.6
		1.0